## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start Date | Due Date | Late | Completed Date | Completed By | Description | Completed Checklist Items | Checklist Items | Labels
w70B63zUSkqpqlry7syS7IIAC1q1 | Re-assess team long and short term goals | To do | Not started | Medium | Hammerly, John - NRCS, Indianapolis, IN | Hammerly, John - NRCS, Indianapolis, IN | 10/14/2021 |  | 10/26/2021 | false
j_IAC-TfMUC51dB-xHFy8YIAESLU | Release Pedon data to public | To do | In progress | Medium |  | Hammerly, John - NRCS, Indianapolis, IN | 12/22/2020 |  | 03/23/2021 | true |  |  |  | 0/4 | Create the database in a test environment;Design Point Database Structure;Develop point data QC & QA standards;Draft Requirements
MixQ48lj_UyYPA-I_0KMAIIAEsBZ | Upgrade OSD database | To do | In progress | Medium |  | Hammerly, John - NRCS, Indianapolis, IN | 12/22/2020 |  | 07/26/2022 | false |  |  |  | 1/1 | Stand up the OSD sub-team
uAulu4zOM0KJmThsjm4hHYIABq2C | Correct NASIS legend ownerships | To do | Not started | Medium |  | Hammerly, John - NRCS, Indianapolis, IN | 12/22/2020 |  | 12/31/2021 | false
S2y3zM955UqGKYVKGGXZx4IAAO2E | Assess scope of NASIS data integrity issues | To do | Not started | Medium |  | Hammerly, John - NRCS, Indianapolis, IN | 12/22/2020 |  | 01/25/2022 | false
9jAQ9KZCg0yaEIMjUhQBPIIABQBy | Website improvements | To do | Completed | Medium |  | Hammerly, John - NRCS, Indianapolis, IN | 12/22/2020 |  | 01/26/2021 | false | 10/14/2021 | Hammerly, John - NRCS, Indianapolis, IN
NM4vYiyAOEuoq-K9VJO-ooIAGkKY | Meet to Discuss delivery of raster soil survey products via SDA | To do | Completed | Medium | Wing, Dan - NRCS, St. Paul, MN;Stephens, Kyle - FPAC-NRCS, Portland, OR | Hammerly, John - NRCS, Indianapolis, IN | 01/27/2021 |  | 02/23/2021 | false | 10/14/2021 | Hammerly, John - NRCS, Indianapolis, IN
DJyFN97prEuJZeLVGTTH-4IAH1Ja | Region Letter | To do | Completed | Medium | Hammerly, John - NRCS, Indianapolis, IN;Thomas, Jeff - NRCS, Morgantown, WV;Stephens, Kyle - FPAC-NRCS, Portland, OR | Hammerly, John - NRCS, Indianapolis, IN | 03/23/2021 | 05/03/2021 | 05/03/2021 | false | 10/14/2021 | Hammerly, John - NRCS, Indianapolis, IN

## Plan name
Plan name | Tasks
Plan ID | CExRvzpyQkGDENoz6exq7YIACSEe
Date of export | 10/14/2021